## Sheet1
	Tasks	Duration	Assigned to
MANAGEMENT	planning	1 day	Saja
	estimated bill	1 day	Saja
CONCEPTION	database conception	1 day	Saja
	SQL scripts	1 day	Saja
	website mockup	1 day	Rowan, Thomas
FRONT END	HTML pages implementation	3 days	Thomas
	search bar	1 day	Rowan
	SEO (search engine optimisation)	1 day	Rowan
	AJAX page refreshing	1 day	Thomas, Saja
BACK END	form processing	2 days	Quentin
	features implementation	5 days	Everyone
	servers configuration	3 days	Thomas
	REST API implementation	2 days	Thomas, Saja, Quentin
	forms and API security	1 day	Quentin, Rowan